## Product backlog
Product Backlog
|  | Organization | LBS
|  | Project | Real time sign language recognition system using cnn
|  | Scrum Master | Fathimath Nahida
|  | Product Owner | PG19IT04
Story ID | Category | Title | User story
1 | Data Collection | Data Set Collection | Collect data set of sign images from various online sources like kaggle
2 | Plan | Project Architecture | Create a user friendly model that can be easily understood and operated
3 | Develop | User Registration | Unique ID for each user
4 | Develop | UI | The platform must have tools that help the user to convert signs into meaningful sentences, such as audio or texts, so that the user can learn sign language in a comfortable environment.
5 | Develop | Admin login | Admin user ID and password set
6 | Design | Learning Strategy | Platform must have interactive and engaging course materials, so that the user can stay interested in learning process.
7 | Sort | Sorting Data set | Sort the collected data set and classify them into required sections
9 | Develop | Assesment Test | Assesment test inorder to measure the level of understanding of user
10 | Develop | Suggestion | feedback functionality for user friendly environment
11 | Develop | Complaint | Complaint functionality to users for reporting faults
12 | Updation | Progress Tracking | Track the progress of the user based on assesment result to indicate their level of understanding
13 | Test | Testing | A well trained sysytem with high accuracy
14 | Train | Train the machine | Trained machine that can deliver curated sign content for users and regulate the speed of content covered

## Sprint 1
Sprint #1Tracking Sheet
|  | Project | Real time sign language recognition system using cnn
|  | Sprint # | 1 |  | Start date |  |  | 2023-02-17
|  | Sprint focus | Design
Remaining units
|  |  |  | week 1 |  |  |  |  | week 2
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Task ID | Story ID | Description | Initial estimate | 2023-02-17 | 2023-02-20 | 2023-02-21 | 2023-02-22 | 2023-02-23 | 2023-02-24 | 2023-02-27 | 2023-02-28 | 2023-03-01 | 2023-03-02
1 | 1 | software installation | 48 | 2 | 0 | 0 | 0 | 0 | 0 | 0
2 | 2 | Develop project architecture | 7 | 0 | 2 | 0 | 0 | 0 | 0 | 0
3 | 3 | User page creation | 8 | 0 | 0 | 2 | 0 | 0 | 0 | 0
4 | 7 | Data set collection | 12 | 0 | 0 | 0 | 2 | 0 | 0 | 0
5 | 6 | Model creation | 13 | 1 | 0 | 0 | 0 | 0 | 0 | 0
6 | 6 | Develop learning strategy | 8 | 0 | 1 | 1 | 1 | 0 | 0 | 0
7 | 7 | Create learning contents | 15 | 0 | 1 | 1 | 0 | 0 | 0 | 0
8 | 7 | Lesson creation | 12 | 0 | 0 | 0 | 0 | 1 | 0 | 0
|  | Remaining units (actual) | 123 | 3 | 4 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0
|  | Remaining units (ideal) |  | 110.7 | 98.4 | 86.1 | 73.8 | 61.5 | 49.2 | 36.9 | 24.6 | 12.3 | 0
|  | Velocity |  | 120 | -1 | 0 | 1 | 2 | 1 | 0 | 0 | 0 | 0
[12 empty] | 0 | 123
[12 empty] | 10 | 0

## Sprint 2
Sprint #2Tracking Sheet
|  | Project | Real time sign language recognition system using cnn
|  | Sprint # | 2 |  | Start date |  |  | 2023-03-03
|  | Sprint focus | Develop
Remaining units
|  |  |  | week 1 |  |  |  |  | week 2
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Task ID | Story ID | Description | Initial estimate | 2023-03-03 | 2023-03-06 | 2023-03-07 | 2023-03-08 | 2023-03-09 | 2023-03-10 | 2023-03-13 | 2023-03-14 | 2023-03-15 | 2023-03-16
1 | 3 | Develop profile | 8
2 | 3 | User profile and dashboard customisation | 16
3 | 6 | Develop list of signs to be provided | 18
4 | 9 | Assesment test | 15
5 | 10 | User progress analytics | 25
6 | 7 | Admin login | 15
|  | Remaining units (actual) | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97
|  | Remaining units (ideal) |  | 87.3 | 77.6 | 67.9 | 58.2 | 48.5 | 38.8 | 29.1 | 19.4 | 9.7 | 0
|  | Velocity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 97
[12 empty] | 10 | 0

## Sprint 3
Sprint #3Tracking Sheet
|  | Project | Real time sign language recognition system using cnn
|  | Sprint # | 3 |  | Start date |  |  | 2023-03-17
|  | Sprint focus | Develop
Remaining units
|  |  |  | week 1 |  |  |  |  | week 2
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Task ID | Story ID | Description | Initial estimate | 2023-03-17 | 2023-03-20 | 2023-03-21 | 2023-03-22 | 2023-03-23 | 2023-03-24 | 2023-03-27 | 2023-03-28 | 2023-03-29 | 2023-03-30
1 | 7 | Suggestion | 14
2 | 7 | Complaint interface | 15
3 | 9 | Assesment | 13
4 | 11 | Integrate ML | 23
5 | 1 | Collect/create suitable train data | 17
6 | 8 | Classification of Dataset | 20
7 | 10 | Progress tracking | 25
|  | Remaining units (actual) | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127
|  | Remaining units (ideal) |  | 114.3 | 101.6 | 88.9 | 76.2 | 63.5 | 50.8 | 38.1 | 25.4 | 12.7 | 0
|  | Velocity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 127
[12 empty] | 10 | 0

## Sprint 4
Sprint #4Tracking Sheet
|  | Project | Real time sign language recognition system using cnn
|  | Sprint # | 4 |  | Start date |  |  | 2023-03-31
|  | Sprint focus | Training and Development
Remaining units
|  |  |  | week 1 |  |  |  |  | week 2
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Task ID | Story ID | Description | Initial estimate | 2023-03-31 | 2023-04-03 | 2023-04-04 | 2023-04-05 | 2023-04-06 | 2023-04-07 | 2023-04-10 | 2023-04-11 | 2023-04-12 | 2023-04-13
1 | 11 | Use model to curate content | 16
2 | 11 | Content creation | 24
3 | 12 | Test curate lessons | 25
4 | 12 | Test accuracy | 20
5 | 12 | User testing | 24
6 | 13 | Feedback collection | 10
7 | 2 | Refine UI/UX | 24
|  | Remaining units (actual) | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143 | 143
|  | Remaining units (ideal) |  | 128.7 | 114.4 | 100.1 | 85.8 | 71.5 | 57.2 | 42.9 | 28.6 | 14.3 | 0
|  | Velocity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 143
[12 empty] | 10 | 0

## Sprint 5
Sprint #5Tracking Sheet
|  | Project | Real time sign language recognition system using cnn
|  | Sprint # | 5 |  | Start date |  |  | 2023-04-14
|  | Sprint focus | Updation and Testing
Remaining units
|  |  |  | week 1 |  |  |  |  | week 2
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Task ID | Story ID | Description | Initial estimate | 2023-04-14 | 2023-04-17 | 2023-04-18 | 2023-04-19 | 2023-04-20 | 2023-04-21 | 2023-04-24 | 2023-04-25 | 2023-04-26 | 2023-04-27
1 | 7 | Addition of more contents | 48
2 | 12 | Final testing | 15
3 | 12 | Quality assurance | 13
4 | 13 | Deployment | 14
5 | 3 | User guide | 10
6 | 2 | Documentation | 15
7 | 6 | Post deployment review | 13
|  | Remaining units (actual) | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128
|  | Remaining units (ideal) |  | 115.2 | 102.4 | 89.6 | 76.8 | 64 | 51.2 | 38.4 | 25.6 | 12.8 | 0
|  | Velocity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 128
[12 empty] | 10 | 0